## Milestones
Engagement Roadmap & Milestones (~12 months)
Cornerstone Community Bank (Nasdaq parent: CCBK) — Information Security & Compliance Program ¦ FDIC · Ohio DFI · SEC ¦ Confidential — NPI // Illustrative
Milestone | Phase | Target | Owner | Status
Program kickoff | 01 | 2026-01-12 | Alvarez | Complete
Foundation & scoping baselined | 01 | 2026-02 | Alvarez | Complete
Asset inventory & data classification | 02 | 2026-02 | Doyle | Complete
GLBA 501(b) risk assessment complete | 03 | 2026-03 | Alvarez | Complete
WISP + policies board-approved | 04 | 2026-04 | Alvarez | Complete
FFIEC / NIST CSF 2.0 assessment | 05 | 2026-06 | Doyle | Complete
SOX ITGC testing complete | 06 | 2026-09 | Barrett | Complete
Vendor reviews + BCP/DR + IR tabletop | 07 | 2026-09 | Nakamura | Complete
Independent penetration test | 08 | 2026-10 | Sharma | Complete
FFIEC IT examination (report) | 08 | 2026-12-15 | Alvarez | Complete
Annual GLBA report to Board | 09 | 2027-01 | Alvarez | Complete
SOX 404 opinion (FY2026 10-K) | 09 | 2027-02 | Barrett | Complete