## Tabletop
IR Tabletop (ransomware / NPI breach, 2026-09) — findings & actions
Cornerstone Community Bank — Third-Party Risk & Business Continuity ¦ 85 vendors · 12 critical/high ¦ Meridian enhanced oversight ¦ 36-hour notification ¦ Confidential — NPI // Illustrative
ID | Finding / Lesson | Severity | Action Item | Owner | Status
TT-1 | IR plan roles needed clearer escalation | Moderate | Update RACI & escalation tree | Alvarez | Complete
TT-2 | 36-hour clock start ambiguous | High | Finalize 36-hour runbook | Alvarez | Complete
TT-3 | Meridian coordination undefined | Moderate | Add vendor IR coordination steps | Nakamura | Complete
TT-4 | Comms templates missing | Low | Build customer/regulator comms templates | Foster | Complete
TT-5 | Backup restore timing unverified | High | Validate restore in DR test | Doyle | Complete
TT-6 | Detection coverage gaps | Moderate | Expand SIEM use cases (Phase 05 roadmap) | Doyle | Open