## Risk Treatment
Risk Treatment Plan — the 8 High risks (priority P1 for Phase 04)
Cornerstone Community Bank — GLBA 501(b) Risk Assessment ¦ 42 risks: 8 High · 18 Moderate · 16 Low ¦ inherent risk overall Moderate ¦ Confidential — NPI // Illustrative
Risk ID | Rating | Treatment | Target Controls (Phase 04) | Owner | Priority
R-01 | High | Mitigate | Phishing-resistant MFA, email security, awareness | Alvarez | P1
R-02 | High | Mitigate | EDR, backups, segmentation, IR plan | Doyle | P1
R-03 | High | Mitigate | Vendor oversight, SOC review, contract controls | Nakamura | P1
R-04 | High | Mitigate | Patch/vuln management, external scanning | Doyle | P1
R-05 | High | Mitigate | Least privilege, PAM, monitoring | Alvarez | P1
R-06 | High | Mitigate | Dual control, callback verification, DLP | Foster | P1
R-07 | High | Mitigate | Enforce MFA everywhere, conditional access | Doyle | P1
R-08 | High | Mitigate | Tested backups, DR runbooks, RTO/RPO | Doyle | P1